## Dashboard
SBC CHECKLIST DASHBOARD
CIP ASSESSMENT
l
|  |  | Planification |  | 28 | 100% | rouge
|  |  | Total Max | 18 | 13 | 46.43% | ver
|  |  | Total obtenu | 0 | 17 | 60.71%
|  |  | Planification | 0% | 18
|  |  | Intervalle de résultat plan |  | 30%
|  |  | 0-59% | Rouge | l
|  |  | 59-79% | Jaune
|  |  | 79-100% | Vert
|  |  | Implementation |  |  | Intervalle de résultat impl |  | 30%
|  |  | Total Max | 22 |  | 0-59% | Rouge | l
|  |  | Total obtenu | 0 |  | 59-79% | Jaune
Planning | Implementation | M&E/KM | Implementation | 0% |  | 79-100% | Vert
0% | 0% | 0%
Nombre d'occurence
|  |  | Yes | Partial | No
|  |  | 0 | 0 | 0 | Planification
|  |  | Yes | Partial | No
|  |  | 0 | 0 | 0 | Implementation
|  |  | Yes | Partial | No
|  |  | 0 | 0 | 0 | ME&KM
|  |  | Yes | Partial | No
|  |  | 0 | 0 | 0 | Total Evaluation
M&E/KM = Monitoring and Evaluation/Knowledge Management
SUMMARY CIP ASSESSMENT
Moyenne
[6 empty] | Résumé | 0%
[6 empty] | 0-54% | Rouge | l
[6 empty] | 54-73% | Jaune
[6 empty] | 73-100% | Vert
MOYENNE(M17;M8;M70)
CIP DEVELOPMENT
Intervalle de résultat
|  |  | 0-59% | Rouge | l
|  |  | 59-81% | Jaune
|  |  | 81-100% | Vert
|  |  | Total Max | 28
|  |  | Total obtenu | 0
|  |  | ME&KM | 0%
Intervalle de résultat
|  |  | 0-46% | Rouge | l
|  |  | 46-61% | Jaune
|  |  | 61-100% | Vert
|  |  | Analyse |  | 22
|  |  | Total Max | 22 | 13
|  |  | Total obtenu | 0 | 17
|  |  | Analyze | 0% | 18
Intervalle de résultat
|  |  | 0-59% | Rouge | l
|  |  | 59-81% | Jaune
|  |  | 81-100% | Vert
Développement Stratégie
|  |  | Total Max | 34
|  |  | Total obtenu | 0
|  |  | Strategy | 0%
Intervalle de résultat
|  |  | 0-59% | Rouge
Intervalle de résultat
|  |  | 0-59% | Rouge | l
|  |  | 59-81% | Jaune
|  |  | 81-100% | Vert
Conception
|  |  | Total Max | 22
|  |  | Total obtenu | 0
|  |  | Messages | 0%
SUMMARY CIP DEVELOPMENT |  |  | Intervalle de résultat
|  |  | 0-59% | Rouge | l
|  |  | 59-81% | Jaune
|  |  | 81-100% | Vert
Mise en oeuvre
|  |  | Total Max | 22
|  |  | Total obtenu | 0
|  |  | Implementation | 0%
Intervalle de résultat
|  |  | 0-59% | Rouge
|  |  | 59-81% | Jaune
|  |  | 81-100% | Vert
|  |  | Total Max | 26
|  |  | Total obtenu | 0
|  |  | ME&GS | 0%
Intervalle de résultat
|  |  | 0-46% | Rouge | l
|  |  | 46-61% | Jaune
|  |  | 61-100% | Vert
Nombre d'occurence
[7 empty] | Yes | Partial | No
[7 empty] | 0 | 0 | 0 | Analyse
[7 empty] | Yes | Partial | No
[7 empty] | 0 | 0 | 0 | Conception
[7 empty] | Yes | Partial | No
[7 empty] | 0 | 0 | 0 | Message
[7 empty] | Yes | Partial | No
[7 empty] | 0 | 0 | 0 | Mise en oeuvre
[7 empty] | Yes | Partial | No
[7 empty] | 0 | 0 | 0 | ME&GS
[7 empty] | Yes | Partial | No
[7 empty] | 0 | 0 | 0 | Total Evaluation
Moyenne
[7 empty] | Résumé | 0%
Intervalle de résultat
[6 empty] | 0-59% | Rouge | l
[6 empty] | 59-81% | Jaune
[6 empty] | 81-100% | Vert
MOYENNE(N171;N161;N151;N86;N77)
l
l
l
l
GENERAL SUMMARY
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
l
l
0%
0%
l
l
l
0%
0%
l
0%
0%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
0%

## Introduction
SBC CHECKLIST TO DEVELOP AND ASSESS COSTED IMPLEMENTATION PLANS
Who is this checklist for?
The SBC Checklist to Develop and Assess Costed Implementation Plans (CIPs) for Demand Creation (DC) interventions is intended to help governments, donors, and planning, and implementation teams. The objective is to ensure that the best practices in terms of social and behavior change (SBC) are strategically integrated with the consideration of singular axes such as gender and young people. It describes the key elements including consideration during evaluation, development, implementation, and monitoring, which is a major factor in the success of SBC interventions in a CIP. This checklist informs users via a series of questions focused on best practices and High Impact Practices (HIP) during the planning, design, implementation, and monitoring and evaluation (M&E) of SBC activities for family planning and reproductive health (FP/RH). Taking the questions into account makes it possible to have a CIP document technically in phase with these best practices in SBC, which increases the chances of achieving the desired results in creating demand. The SBC checklist can be used by work teams throughout the process of developing and launching a new CIP or assessing an already existing CIP.
How to use this checklist
To use the Assessment Checklist for the development and evaluation of a CIP, read each question and determine if each criterion was met completely (yes), partially (partially), or not met at all (no). • A "yes" answer indicates alignment with a criterion and a score of 2. • A "partial" response suggests that the criterion has not been fully met and a score of 1. • A "no" answer indicates that the criterion was not followed or applied and a score of 0. In the last two cases, the Comments column explains the answer or suggest the necessary adjustments to obtain a "yes" answer. Whatever the answer, especially if it is "partial" or "no", the team must refer to the Recommendations column via the link that points to the recommendation, or directly access the Recommendations sheet by following the number of the recommendation (Example: R-1-1 or R-3-4). Some recommendations provide access to additional resources to implement it. A dashboard allows you to visually assess the results of the assessment or development. For the assessment: The analysis, implementation, and follow-up phases of evaluation and knowledge management are assessed graphically in three ways: • Globally in the Summary section through a graphical representation in Gauge expressed as a percentage (%). • In a detailed way through a histogram representation of the number of Yes, Partial, and No. The red color represents the answer No, the yellow color Partial, and the green color represents the answer Yes. For the elaboration The analysis, strategy, design, implementation, and M&E and KM phases are assessed graphically in three ways: • Globally in the Summary section through a graphical representation in the Gauge, expressed as a percentage (%). • In a detailed way through a histogram representation of the number of Yes, Partial, and No. The red color represents the answer No, the yellow color Partial, and the green color represents the answer Yes. For more information, please consult the Guide to the SBC Checklist.
This tool is made possible by the generous support of the American people through the United States Agency for International Development (USAID). The content is the responsibility of Breakthrough ACTION and does not necessarily reflect the views of USAID or the United States government.

## CIP Assessment
CIP ASSESSMENT CHECKLIST
NB: messages/materials and broadcasts/productions. Please specify details in the comment field.
No. | Evaluation criteria | Yes | Partial | No | Notes | Recommendations
1. PLANNING AND COORDINATION
1 | Are DC activities the result of a global strategy/SBC plan/communication? |  |  |  |  | R-1-1
2 | Have DC activities benefited from a monitoring plan? |  |  |  |  | R-1-2
3 | Have DC activities benefited from an evaluation plan? |  |  |  |  | R-1-3
4 | Has there been any formative research for the implementation of a CIP DC activities? |  |  |  |  | R-1-4
5 | Have all DC activities taking place in the country been aligned with the CIP? |  |  |  |  | R-1-5
6 | Was gender taken into account during development? |  |  |  |  | R-1-6
7 | Were young people specifically taken into account when drawing up a CIP (associates)? |  |  |  |  | R-1-7
8 | Was stakeholder capacity building in SBC taken into account during the preparation of a CIP? |  |  |  |  | R-1-8
9 | Have DC activities benefited from a knowledge management plan? |  |  |  |  | R-1-9
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL PLANNING AND COORDINATION |  | 0 | 0 | 0
2. IMPLEMENTATION
1 | Have all DC activities carried out in the country been aligned with priority behaviors? |  |  |  |  | R-2-1
2 | Did DC activities specifically concern the young target? |  |  |  |  | R-2-2
3 | Was the dissemination/production of messages/materials based on all the priority targets of a CIP? |  |  |  |  | R-2-3
4 | During the implementation of DC activities, was there a follow up or meetings around the post-service period in terms of the monitoring of discontinuation using methods? |  |  |  |  | R-2-4
5 | During the implementation of DC activities, was there a follow-up or meeting around the post-service period in terms of monitoring side effects? |  |  |  |  | R-2-5
6 | Has the quality of messages/materials been assessed before their dissemination/dissemination (pre-test)? |  |  |  |  | R-2-6
7 | Has the quality of the messages/materials been assessed after their dissemination/dissemination? |  |  |  |  | R-2-7
8 | Has the capacity building of stakeholders in SBC been effective? |  |  |  |  | R-2-8
9 | Have technological innovations been used to convey FP/RH messages? |  |  |  |  | R-2-9
10 | Did the implementation take into account gender aspects? |  |  |  |  | R-2-10
11 | During the implementation of the DC activities, did any knowledge management activities take place? |  |  |  |  | R-2-11
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL IMPLEMENTATION |  | 0 | 0 | 0
3. MONITORING AND EVALUATION/KNOWLEDCE MANAGEMENT
1 | Have the performance indicators in a CIP dashboard been monitored for updating DC activities? |  |  |  |  | R-3-1
2 | Were there follow-up meetings around CIP DC activities during implementation? |  |  |  |  | R-3-2
3 | Has the coordination of DC activities been assessed? |  |  |  |  | R-3-3
4 | Overall, has the implementation of DC activities been specifically assessed, particularly in the social and behavioral dimensions? |  |  |  |  | R-3-4
5 | Did the assessments differentiate the priority targets? |  |  |  |  | R-3-5
6 | Have the related aspects of the young target been specifically assessed? |  |  |  |  | R-3-6
7 | Has each action plan (annual plan or implementation phase) been evaluated? |  |  |  |  | R-3-7
8 | Have the budgets for activities drawn from or aligned with a CIP been documented after the meeting to mobilize resources and define the gaps? |  |  |  |  | R-3-8
9 | Has the number of messages/materials produced been documented? |  |  |  |  | R-3-9
10 | The number of messages/material broadcasts/distributions documented? |  |  |  |  | R-3-10
11 | Have gender aspects been measured? |  |  |  |  | R-3-11
12 | Have the interventions deemed high-impact or innovative been shared in national and or international conferences? |  |  |  |  | R-3-12
13 | Have knowledge management activities been evaluated? |  |  |  |  | R-3-13
14 | Has the SBC indicator bank been used for better monitoring of activities? |  |  |  |  | R-3-14
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL MONITORING AND EVALUATION/KNOWLEDCE MANAGEMENT |  | 0 | 0 | 0
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does NB stand for? Please spell out if it is not explained on this sheet elsewhere.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All of these links are not working. Not sure if it's just this version or the formula/link needs to be recreated.

## Recommendations
CIP ASSESSMENT CHECKLIST: LIST OF RECOMMENDATIONS
Regarding messages/materials and broadcasts/productions: please specify details in the comment field.
No. | Evaluated criteria | Recommendations | Reference material
PLANNING AND COORDINATION
R-1-1 | Are DC activities the result of a global strategy/SBC plan/communication? | Yes: Update this plan (if it is currently valid) to integrate the latest data. Partial: Evaluate this plan and take into consideration the conclusions of this assessment in the new planning. No: Develop an SBC strategic plan using a systematic strategic planning tool such as the P Process. This plan is ideally annexed to a validated FP/RH strategic plan. | P process
R-1-2 | Have DC activities benefited from a monitoring plan? | Yes: Update this plan to integrate the latest data. Partial: Update this plan to integrate the latest data and fill in the gaps. No: Develop a follow-up plan for the new CIP. The plan should be in phase with the monitoring and evaluation plan of the valid SBC strategic plan.
R-1-3 | Have DC activities benefited from an evaluation plan? | Yes: Update this plan to integrate the latest data. Partial: Update this plan to integrate the latest data and fill in the shortcomings. No: Develop an evaluation plan for the new CIP. The plan should be in phase with the monitoring and evaluation plan of the valid SBC strategic plan.
R-1-4 | Has there been any formative research for the implementation of DC activities within the CIP? | Yes: Verify the need for further formative research based on available data and identified problems. Partial: Carry out additional research so that interventions can be truly evidence-based and complete. No: Do formative research to strengthen understanding of targets, behavioral problems. | Formative research
R-1-5 | Have all DC activities taking place in the country been aligned with the CIP? | Yes: Evaluate the coordination of interventions between the stakeholders and take into account the recommendations in the new planning. Partial: Strengthen the coordination meetings between the stakeholders in the field to that everyone is part of the achievement of national objectives. In particular, coordination/advocacy activities with potential donors are essential to ensure that new programs take into account the country's objectives and commitments. No: The coordination section of a CIP must be sufficiently documented (assessed to understand the reasons for the non-alignment). Then the new planning must stick to the implementation of the planned actions. These must be regularly followed up in coordination meetings so that the efforts of the stakeholders do not dissipate and contribute to the achievement of the objectives of a CIP.
R-1-6 | Was gender taken into account during development? | Yes: Evaluate the gender aspects (at all phases) take into account the recommendations in the new planning. Partial: Evaluate the gender aspects and follow the recommendations in the new planning. No: Carry out new Gender and FP/RH research and integrate, implement, and follow the recommendations in the new planning.
R-1-7 | Were young people specifically taken into account when drawing up the CIP ? | Yes: Evaluate the aspects of integration of young people as actors and beneficiaries and take into account the recommendations in the new planning. Partial: Evaluate the aspects of integration of young people as actors and beneficiaries, integrate, implement and follow the recommendations in the new planning. No: Carry out new research on young people and FP/RH and integrate, implement, and monitor the recommendations in the new CIP.
R-1-8 | Was stakeholder capacity building in SBC taken into account during the preparation of the CIP? | Yes: Evaluate the capacity building plan, assess the capacities of stakeholders, and take into account the recommendations in the new planning. Partial: Evaluate the capacity building plan, assess the capacities of the stakeholders, and take into account the recommendations in the new planning. No: Assess the capacities of the stakeholders and take into account the recommendations in the new planning. | SBC Evaluation
R-1-9 | Have DC activities benefited from a knowledge management plan? | Yes: Evaluate the process and strengthen the level of consideration of knowledge management activities throughout the new planning process. Partial: Evaluate and take into account results of the assessment of knowledge management aspects in the new planning. No: Develop a clear knowledge management plan; it should be an integral part of the new CIP. | KM Kit
IMPLEMENTATION
R-2-1 | Have all DC activities carried out in the country been aligned with priority behaviors? | Yes: Based on the data, review the priority behaviors for new planning. Partial: Evaluate the process and the interventions, do new research for a better definition of behaviors, and take into account the recommendations in the new planning. No: Do new research for a better understanding of behaviors, prioritize them, integrate, implement, and monitor the results in the new planning. | Targeting
R-2-2 | Did DC activities specifically concern the young target? | Yes: Evaluate the aspects of the implementation of the activities of the young target and take into account the recommendations in the new planning. Partial: Evaluate the aspects of the implementation of the activities of the young target and take into account the recommendations in the new planning. No: Carry out new research on young people and FP/RH; integrate, implement, and follow the recommendations in the new CIP.
R-2-3 | Were the dissemination/production of messages/materials based on all the priority targets of the CIP? | Yes: Evaluate the impact of the messages and take into account the recommendations in the new planning. Partial: Evaluate the process and the impact of the messages, rethink the segmentation of targets to start from the data, and take into account the recommendations in the new planning. No: Conduct research for a better understanding of key behaviors, priority targets and integrate, implement, and follow the recommendations in the new CIP.
R-2-4 | During the implementation of DC activities, were there follow-up meetings around the post-service period in terms of monitoring dropouts? | Yes: Evaluate the process and the strategies developed to further reduce dropouts and take into account the conclusions in the new planning. Partial: Evaluate the strategies developed to reduce dropouts and take the conclusions into account in the new planning. No: Do research to better understand dropouts, develop strategies for their reduction, integrate them, implement them, and monitor the results in the new CIP.
R-2-5 | During the implementation of DC activities, was there a follow-up or meeting around the post-service period in terms of monitoring side effects? | Yes: Evaluate the strategies developed for the management of side effects and take into account the conclusions in the new planning. Partial: Evaluate the process and the strategies developed to better manage the issues related to side effects and take into account the conclusions in the new planning. No: Do research to better understand the issues related to side effects, develop strategies for their reduction, integrate them, implement them, and monitor the results in the new planning.
R-2-6 | Has the quality of messages/materials been assessed before their dissemination/dissemination (pre-test)? | Yes: Evaluate and strengthen the process in the new CIP. Partial: Evaluate the process and take into account the conclusions of this evaluation in the new CIP. No: Put in place the mechanisms, tools and systematically pre-test the messages/materials of the interventions of the new CIP. | Pre-test guide
R-2-7 | Has the quality of the messages/materials been assessed after their dissemination/dissemination? | Yes: Evaluate and strengthen the process in the new CIP. Partial: Evaluate the process and take into account the conclusions of this assessment in the new CIP. No: Put in place mechanisms, tools and systematically assess the impact of messages/materials of interventions. This can be as part of an overall evaluation, but the impact of messages on targets should be systematically evaluated in the new CIP to ensure their effectiveness.
R-2-8 | Has the capacity building of stakeholders in SBC been effective? | Yes: Evaluate the process, update the SBC capacity building needs of stakeholders, and take into account the results of the assessment and the needs in the new planning. Partial: Evaluate the process, update the capacity building needs of stakeholders, and take into account the results of the assessment and the needs in the new planning. No: Assess the stakeholders' SBC capacities and take the results into account in the new planning.
R-2-9 | Have technological innovations been used to convey FP/RH messages? | Yes: Evaluate and strengthen their level of use in the implementation of activities. Partial: Evaluate and take into account the results of the evaluation in the new planning. No: Evaluate the need and needs for using technological innovations to achieve results. Take into account the results of the evaluation in the new planning.
R-2-10 | Did the implementation take into account gender aspects? | Yes: Evaluate the process and strengthen the level of gender mainstreaming throughout the new planning process. Partial: Evaluate and take into account the results of the evaluation in the new planning. No: Do research on the obstacles linked to gender in FP/RH and take into account the results of the research in the new CIP. | Take gender into account
R-2-11 | During the implementation of the DC activities, did any knowledge management activities take place? | Yes: Evaluate the process and strengthen the level of consideration of knowledge management activities throughout the new planning process. Partial: Evaluate and take into account results of the assessment of knowledge management aspects in the new planning. No: Develop a clear knowledge management plan, it should be an integral part of the new plan.
MONITORING AND EVALUATION/KNOWLEDCE MANAGEMENT
R-3-1 | Have the performance indicators in a CIP dashboard been monitored for updating DC activities? | Yes: Strengthen this connection between the dashboard and the monitoring of activities so that they can have the best strategic and operational orientations. Partial: Evaluate the activity review process in line with the dashboard of indicators and take into account the results of this assessment in the new planning. No: Systematically integrate the review of activities in line with the dashboard indicators and take into account the results of this assessment in the new planning.
R-3-2 | Were there follow-up meetings around CIP DC activities during implementation? | Yes: Evaluate the process during a meeting and take into account the conclusions of this evaluation in the new planning. Partial: Evaluate the process during a meeting and take into account the conclusions of this evaluation in the new planning. No: Systematically plan, implement and document the follow-up meetings of DC activities.
R-3-3 | Has the coordination of DC activities been assessed? | Yes: Take into account the recommendations of the evaluation for further coordination of DC activities. Partial: Evaluate the process of coordination between stakeholders, take into account the recommendations of the evaluation for further coordination of DC activities. No: Evaluate the process of coordination between stakeholders take into account the recommendations of the evaluation for further coordination of DC activities.
R-3-4 | Overall, has the implementation of DC activities been specifically assessed, particularly in the social and behavioral dimensions? | Yes: Take into account the recommendations of the evaluation for further coordination of DC activities. Partial: Evaluate the impact of demand creation activities on the behavior of the targets, on social standards to ensure that those have effectively given the expected results, take into account the recommendations of the evaluation in the new CIP. No: Evaluate the impact demand creation activities on the behavior of targets, on social standards to ensure that those have effectively given the expected results, take into account the recommendations of the evaluation in the new CIP.
R-3-5 | Did the assessments differentiate the priority targets? | Yes: Take into account the conclusions of this evaluation to further determine and target the priority targets in the new CIP. Partial: Evaluate the major changes in each priority to comply take into account the recommendations of that in the definition and the manner of reaching the new priority targets in the new CIP. No: Evaluate the major changes in each priority to take into account the recommendations of that in the definition and how to achieve the new priority targets in the new CIP.
R-3-6 | Have the related aspects of the young target been specifically assessed? | Yes: Take into account the conclusions of this evaluation to involve and target more young people in the process and interventions of DC in the new CIP. Partial: Evaluate the process and interventions targeting young people, take into account the conclusions of this evaluation to involve and target more young people in the process and interventions of the new CIP. No: Evaluate the process of involvement and impact of DC interventions among young people to take into account the recommendations of this evaluation in the prioritization of targets, the involvement of young people in the development, implementation, and monitoring of activities in the new CIP.
R-3-7 | Has each action plan (annual plan or implementation phase) been evaluated? | Yes: Make the overall conclusions of the various annual evaluations on DC activities to better build the lines of intervention of the new CIP. Partial: Make a collective review of the different plans if an overall assessment of a CIP has not been made, take into account the conclusions of this review in the preparation of the new CIP while systematically integrating periodically the review/evaluation of DC activities. No: Make a collective review of the different plans if an overall assessment of a CIP has not been carried out, take into account the conclusions of this review in the preparation of the new CIP while systematically integrating periodically review/evaluation of DC activities.
R-3-8 | Have the budgets for activities drawn from or aligned with a CIP been documented after the meeting to mobilize resources and define the gaps? | Yes: Strengthen the documentation process to have the best possible financial projections for the new CIP. Partial: Make a collective review of the different plans if an overall assessment of a CIP has not been carried out, take into account the conclusions of this review in the preparation of the new CIP while systematically integrating periodically the review/evaluation of DC activities. No: Make a collective review of the different plans if an overall assessment of a CIP has not been carried out, take into account the conclusions of this review in the development of the new CIP.
R-3-9 | Has the number of messages/materials produced been documented? | Yes: Strengthen the process of documentation of messages/materials developed for better coordination in the new CIP. Partial: Evaluate the process of documentation and production of messages/materials for DC activities, take into account the recommendations for the development of the new CIP. No: Evaluate the process of documentation and production of messages/materials for DC activities, take into account recommendations for the development of the new CIP.
R-3-10 | The number of messages/material broadcasts/distributions documented? | Yes: Strengthen the process of documenting messages/materials disseminated/disseminated for better coordination in the new CIP. Partial: Evaluate the documentation process for dissemination/dissemination of messages/materials of DC activities, take into account the recommendations for the elaboration of the new CIP. No: Evaluate the process of documentation dissemination/dissemination of messages/materials of DC activities, take into account the recommendations for the development of the new CIP.
R-3-11 | Have gender aspects been measured? | Yes: Take into account the recommendations of the evaluation throughout the process of drawing up the new CIP. Partial: Evaluate and take into account the results of evaluation in the new planning. No: Evaluate and take into account the results of the evaluation in the new planning.
R-3-12 | Have the interventions deemed high-impact or innovative been shared in national and or international conferences? | Yes: Evaluate the process and strengthen the level of sharing of experiences and results in the new CIP. Partial: Evaluate and take into account the results of the evaluation in the new planning. No: Develop a content production plan to share with other countries or regions of the same country. This plan is an integral part of the knowledge management plan.
R-3-13 | Have knowledge management activities been evaluated? | Yes: Evaluate the process and strengthen the level of consideration of the knowledge management activities of DC activities in the whole process of the new planning. Partial: Evaluate and take into account the results of the evaluation of knowledge management aspects of DC activities in the new planning. No: Develop a clear plan for knowledge management of DC activities, it must be part of the new plan.
R-3-14 | Has the database of SBC indicators been used for better monitoring of activities? | Yes: Evaluate the process of setting SBC indicators and then strengthen them by drawing inspiration from the elements put in the bank of social indicators and behavior change for FP/RH and service delivery. Partial: Evaluate the process of setting SBC indicators and then strengthen them by drawing inspiration from the elements put in the bank of social indicators and behavior change for FP/RH and service delivery. No: Develop an indicator table based on the elements put in the bank of social indicators and behavior change for FP/RH and service delivery.

## Analyze
CIP ELABORATION CHECKLIST: ANALYSIS
No. | Criteria | Yes | Partial | No | Comment | Resources
1 | Does the situation analysis plan to examine (national, regional, and local level) FP/RH knowledge, attitudes, norms, and behaviors?
2 | Does the situational analysis anticipate to examine (national, regional, and local level) the social, economic, political, and health context in FP?
3 | Does the situational analysis anticipate to examine the media context?
4 | Does the situation analysis plan to examine (national, regional, and local level) the coordination of DC activities?
5 | Does the situational analysis plan to characterize (national, regional, and local level) specific groups of young people, providers, religious, displaced/refugees?
6 | Does the situational analysis anticipate to examine (national, regional, and local level) technical and operational capacities in DC?
7 | Does the situation analysis plan to examine (national, regional, and local level) gender issues in FP?
8 | Does the situational analysis anticipate to examine the current state of communications activities prior to service delivery?
9 | Does the situational analysis anticipate to examine the current state of communication activities during service delivery?
10 | Does the situational analysis plan to review the current state of post-service communications activities?
11 | Does the situational analysis anticipate to examine the digital context?
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL ANALYSIS |  | 0 | 0 | 0

## Strategy Development
CIP ELABORATION CHECKLIST: STRATEGIC DESIGN
No. | Criteria | Yes | Partial | No | Comment | Resources
1 | Is the DC strategy based on revising a strategy based on a systematic SBC process to guide the design, implementation, and monitoring and evaluation of interventions? |  |  |  |  | Processus P
2 | Are the development of CIP's DC activities based on a theory of change? |  |  |  |  | Théories dans le CSC
3 | Is the strategy developed for DC activities much more focused on attitudes and behaviors than on knowledge?
4 | Does the defined strategy take gender aspects into account? |  |  |  |  | Prendre en compte le genre
5 | Does audience segmentation go beyond demographics such as age, place of residence, and gender to include other psychographic variables such as attitudes, values, social norms, lifestyles, and communication preferences? |  |  |  |  | Segmentation des cibles
6 | Is there a specific strategy, or activities targeting young people? |  |  |  |  | Elaboration d'une stratégie jeunes
7 | Is there a clearly defined strategy of activities before the use of FP/RH services?
8 | Is a clearly defined strategy of activities while using FP/RH services? |  |  |  |  | Intégration CSC dans l'offre de service
9 | Is there a clearly defined strategy of activities after using FP/RH services?
10 | Are past DC experiences used for the definition of DC activities sufficiently documented (strategy, implementation plan, monitoring, and evaluation plan, final evaluation results)
11 | Do the planned activities individually or collectively address all of the designated priority targets?
12 | Are the planned DC activities reaching vulnerable, marginalized, and hard-to-reach populations to reduce the economic, social, cultural, and geographic barriers that hinder their access to FP?
13 | Do the planned DC activities take into account technological innovations adapted to priority targets? |  |  |  |  | CSC et Digital Health (PHI)
14 | Does the development of the strategy take into account the technical and operational capacities of the stakeholders? |  |  |  |  | Evaluation des capacités en CSC
15 | Is a clear knowledge management strategy defined?
16 | Are there any activities due to their relevance/innovation that will be documented and shared at national and or international conferences?
17 | Are the selected activities part of the High Impact Practices? |  |  |  |  | Pratiques à Haut Impact (PHI)
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL STRATEGY DEVELOPMENT |  | 0 | 0 | 0
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All link names need to be changed to English versions.

## Messages Design
CIP ELABORATION CHECKLIST: DESIGN OF MESSAGES
No. | Criteria | Yes | Partial | No | Comment | Resources
1 | Does the choice of channels take into consideration audience analysis, channel analysis |  |  |  |  | Utilisation des canaux mixte (PHI masse média)
2 | Does the choice of channels take into account the theory of change?
3 | Are the messages developed on the priority problem behavior list?
4 | Are the messages pre-tested? |  |  |  |  | Guide Pre-test
5 | Do the developed messages take into account all the priority targets?
6 | Do the messages developed specifically take into account the young target?
7 | Is the development of messages subject to a systematic consensual review according to accepted SBC rules such as that of the 7Cs?
8 | Do the developed messages take into account the gender aspects found in the analysis phase?
9 | Do the developed messages take into account marginalized targets such as displaced persons/refugees or other key populations?
10 | Do the messages developed specifically take into account the target provider?
11 | Do the messages developed specifically take into account the post-service period?
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL MESSAGES DESIGN |  | 0 | 0 | 0
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Links need to be in English where possible.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I am familiar with 3Cs but not 7. Does this need a resource link or further explanation? Reply: I dont know that CCP has a resource that is uniquely and specifically for the 7 Cs, but I was able to find some resources that reference and talk about the 7 Cs, among other things. What do you think about this: https://thecompassforsbc.org/how-to-guide/how-develop-sbcc-creative-materials

## Implementation
CIP ELABORATION CHECKLIST: IMPLEMENTATION
No. | Criteria | Yes | Partial | No | Comment | Resources
1 | Is an implementation plan clearly defined with the definition of activities, roles, and responsibilities of stakeholders?
2 | Does the implementation plan take into account post-service period monitoring meetings/activities (management of dropouts, management of side effects)?
3 | Is an upgrading of the technical and operational capacities of the stakeholders planned for effective implementation of the activities?
4 | Has an integrated media plan been developed?
5 | Are the broadcasts based on the analysis of the environment and the media consumption habits of the targets?
6 | Are target-appropriate digital channels used for broadcasts?
7 | Does the implementation of the activities use a combination of channels to reach more people?
8 | Does the implementation of activities specifically take young targets into account?
9 | Does the implementation of activities take gender into account?
10 | Does the activity update take into account the results of new research?
11 | Are the knowledge management and practice sharing activities clearly defined?
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL IMPLEMENTATION |  | 0 | 0 | 0

## Monitoring
CIP ELABORATION CHECKLIST: MONITORING & EVALUATION/KNOWLEDCE MANAGEMENT
No. | Criteria | Yes | Partial | No | Comment | Resources
1 | Is a DC activity monitoring plan developed (quarterly/annually)? |  |  |  |  | Key indicators for FP and SBC
2 | Is a DC activity evaluation plan developed? |  |  |  |  | Key indicators for FP and SBC
3 | Does the implementation plan take into account post-service period monitoring meetings/activities (management of dropouts, management of side effects)?
4 | Is a clear mechanism for updating DC activities (quarterly and annually) described?
5 | Are follow-up meetings around CIP DC activities planned?
6 | Is a knowledge management plan clearly established with defined practice and experience sharing meetings?
7 | Are gender aspects clearly taken into account in the monitoring and evaluation plan?
8 | Is the inclusion of targets clearly defined in the monitoring and evaluation plan?
9 | Does the monitoring and evaluation plan differentiate the priority targets?
10 | Is there a monitoring and evaluation of the quality of the messages/materials?
11 | Does the monitoring and evaluation plan include an indicator of the capacity building of stakeholders in the different components of the SBC?
12 | Does a monitoring and evaluation plan integrate and characterize the integrated media plan (broadcasts and number of people affected?
13 | Does the monitoring and evaluation plan integrate and characterize multimedia productions, including printed ones?
NUMBER OF ANSWERS |  | 0 | 0 | 0
TOTAL MONITORING, EVALUATION AND KNOWLEDCE MANAGEMENT |  | 0 | 0 | 0